Presented to:

Sadara Chemical Company

Digital & Technology Division

Jubail Industrial City II, Eastern Province, Kingdom of Saudi Arabia

Attn: Faisal Al-Otaibi

VP Procurement & Contracts

Presented By:

Wipro Limited

Enterprise AI Operating System (EOS) – AI-Led Operating Model Transformation RFP Response

©WIPRO

Version 1.0

Table of Contents

1	Executive Summary	3

2	About WIPRO	4

3	Our Understanding of Sadara’s challenges	5

3.1	AS-IS diagram	6

3.2	Problem Statement Perspectives	6

3.2.1	Strategic Context	6

3.2.2	Functional Shortcomings	6

3.2.3	Technical Debt	7

3.3	Impact Summary	8

4	Our Proposed Solution	8

4.1	Enterprise AI Operating System (EOS) – Solution Overview	8

4.2	Proposed Solution Architecture	10

4.2.1	Architecture Philosophy	10

4.2.2	Layer 0 – Hybrid Infrastructure, Cybersecurity & Business Continuity	10

4.2.3	Layer 1 – Source Systems	11

4.2.4	Layer 2 – Connectivity & Integration	12

4.2.5	Layer 3 – Data Ingestion, Cleansing and Governance	13

4.2.6	Layer 4 – Unified Data Lakehouse	14

4.2.7	Layer 5 – Agentic AI Platform	15

4.2.8	Layer 6 – Enterprise Service Bus	16

4.2.9	Layer 7 – Experience Layer	17

4.3	EOS Platform Pillars	18

5	Functional Domain AI solutions	21

6	Implementation Approach	25

6.1	Wave 0 – Foundation & Discovery	26

6.2	Wave 1 – Platform Foundation & Early Value	26

6.3	Wave 2 – AI Scale & Cross-Domain Integration	28

6.4	Wave 3 – Optimization & Autonomous Operations	29

6.5	Alignment with the Outcome based commercial model	30

6.6	Timeline – 60 months	31

7	Delivery & Governance	32

7.1	Multi-Tier Governance	32

7.2	Milestone Gates & Controlled Progression	34

7.2.1	Wave Transition Gate Framework	34

7.2.2	AI Deployment Gate — Add Framing Line	35

7.3	Program Health Dashboard	36

8	Workshop Program	37

8.1	Discovery workshop	37

8.2	Design Thinking Workshop	38

8.3	Architecture workshop	38

8.4	Executive Alignment	38

8.5	Train the Trainer	38

9	Assumptions & Exclusions	39

10	Wipro Team - Tentative	39

11	Center of Excellence	42

12	Change Management	42

12.1	Change Order Governance	43

12.1.1	Change Order Process	43

13	Communication and Coordination	44

14	Ethics, Risks & Responsible AI	45

15	Strategic Advisory	47

16	Commercial Model	48

16.1	WIPRO’s Outcome based commercial philosophy	48

16.2	Commercial structure	48

16.3	ROI Calculation	48

17	Sovereignty & IP Framework	49

17.1	Intellectual Property Ownership	49

17.2	Data sovereignty	49

18	Case Studies & References	50

# Executive Summary

Sadara Chemical Company operates one of the world’s most advanced petrochemical complexes, yet its current technology landscape limits its ability to fully realize a digital-first, AI-led operating model aligned with Saudi Vision 2030.

Today, Sadara faces technology fragmentation, data silos, and reactive decision-making. With over 120 applications, 85,000+ OT data points confined within plant systems, and critical processes such as maintenance, supply chain, and financial close relying on manual intervention, the organization is operating below its full potential. This results in significant business impact, including unplanned downtime costs of up to $1.2M per day per unit and extended financial close cycles.

With increasing global competition, rising operational costs, and regulatory pressure, delaying this transformation will compound inefficiencies and increase risk exposure.

Wipro proposes an Enterprise AI Operating System (EOS), a unified platform designed to transform Sadara into an intelligent, AI-driven enterprise.

This transformation is built on three integrated pillars:

- Unified Data Fabric
A real-time, governed data layer integrating enterprise systems (SAP, Salesforce, Workday) with OT environments (DCS, PI, SCADA), enabling seamless data access across the organization.

- Domain AI Agents
Six domain-specific AI agents across Manufacturing, Supply Chain, Commercial, Finance, HR & Safety, and IT Operations — enabling predictive insights, automation, and optimized decision-making.

- Intelligent Rationalization
A structured approach to reducing application sprawl and technical debt, transitioning from 120+ applications to a streamlined, governed core landscape.

Together, these pillars enable Sadara to shift from reactive operations to real-time, data-driven decision-making, delivering measurable outcomes such as:

- Up to 40% reduction in unplanned downtime

- 3–5 day financial close

- 15–20% inventory optimization

- 60% IT service ticket deflection

Powered by Wipro’s ai360 platform and industry-specific accelerators, this approach is designed as a holistic enterprise transformation, not a collection of disconnected use cases.

Wipro combines deep petrochemical industry expertise, strong SAP and AI partnerships, and a local presence in Saudi Arabia to deliver a scalable, compliant, and future-ready solution. We are committed to partnering with Sadara to enable a sustainable AI-led operating model that drives long-term efficiency, resilience, and competitive advantage.

# About WIPRO

Wipro is a leading global technology services and consulting company specializing in large-scale, AI-led enterprise transformations across complex industrial environments. With deep expertise across AI, cloud, data, and enterprise platforms, Wipro partners with organizations to modernize operations, unlock intelligence from data, and drive measurable business outcomes.

Wipro has made significant investments in artificial intelligence through its ai360 platform, delivering end-to-end capabilities across data, models, agents, and governance. With 600+ AI/ML models in production and a growing library of reusable AI agents across operations, supply chain, finance, and IT, Wipro enables enterprises to move from experimentation to production-scale AI adoption. These capabilities form the foundation of Wipro’s Enterprise AI Operating System (EOS) approach — enabling organizations to transition from fragmented systems to unified, AI-driven operating models.

In the industrial and petrochemical sector, Wipro brings proven experience in OT/IT convergence, predictive maintenance, process optimization, and safety-critical systems — capabilities essential for high-complexity environments such as Sadara’s.

Wipro’s strength is further enhanced through strategic partnerships with leading technology providers, including SAP, Microsoft Azure OpenAI, AWS, Google, and NVIDIA, enabling flexible, scalable, and future-ready architectures.

With a strong regional presence in the Kingdom of Saudi Arabia, Wipro ensures alignment with local regulatory requirements, data residency, and cybersecurity standards, while delivering programs with global best practices and governance.

Why Wipro for Sadara

- Proven delivery of large-scale industrial and petrochemical transformations

- Deep expertise in SAP ecosystems and enterprise integration at scale

- Advanced capabilities in AI, data platforms, and OT/IT convergence

- Pre-built accelerators and AI assets enabling faster time-to-value

- Outcome-based delivery model aligned to measurable business results

- Established delivery presence in Saudi Arabia with global governance standards

# Our Understanding of Sadara’s challenges

Sadara’s challenges are not isolated issues — they are interconnected and compounding across technology, data, and operations. At the core, technology fragmentation has created data silos, limiting the organization’s ability to leverage AI and resulting in a continued reliance on manual, experience-based decision-making.

Across the enterprise, Sadara operates with a complex landscape of over 120 applications and multiple disconnected systems spanning SAP, Salesforce, Workday, ETRM, and OT environments. This fragmentation leads to duplicated data, inconsistent views of the business, and extended process cycles — most notably a financial close that exceeds 10 days and supply chain decisions that are not made in real time.

On the plant floor, 26 manufacturing units generate high-frequency operational data across 85,000+ instrument tags. However, this data remains largely confined within control systems and is not integrated into enterprise decision-making. As a result, maintenance remains calendar-based, process optimization relies on offline models, and operators depend heavily on alarms and institutional knowledge rather than predictive intelligence.

From a business operations perspective, critical functions such as supply chain planning, pricing, workforce management, and financial forecasting are predominantly manual and reactive. Decisions are often based on historical reports rather than real-time insights, limiting Sadara’s ability to respond dynamically to market changes, operational risks, and production variability.

In parallel, Sadara faces significant technical debt. A large portion of the IT budget is consumed by maintaining legacy systems, including an aging SAP ECC environment, custom applications, and overlapping tools across analytics and workflow platforms. This reduces the organization’s capacity to invest in innovation and scale AI initiatives beyond isolated proof-of-concepts.

Additionally, Sadara’s current AI maturity remains at an early stage, with multiple disconnected pilots that have not transitioned into production. Without a unified data foundation, governance model, and enterprise AI platform, these efforts are unable to deliver sustained business value.

Collectively, these challenges result in:

- Limited visibility across operations and data

- Delayed and reactive decision-making

- High operational and maintenance costs

- Increased risk in safety, compliance, and cybersecurity

- Inability to scale AI across the enterprise

Sadara’s opportunity lies in addressing these challenges holistically — by unifying data, reducing technical debt, and enabling AI-driven decision-making across all functional domains.

## AS-IS diagram

The challenges Sadara faces are not isolated incidents - they compound each other. Technology fragmentation creates data silos. Data silos prevent AI. Without AI, Sadara relies on manual decision making in a world that demands real-time intelligence. The result is a business operating below its potential, exposed to regulatory risk, and increasingly dependent on the institutional knowledge of an ageing workforce.

## Problem Statement Perspectives

### Strategic Context

Sadara's strategic mandate - under Saudi Vision 2030 and the Aramco/Dow digital-first directive — requires an AI-led operating model. Currently Sadara falls short of it.

- 8 disconnected AI proof-of-concepts exist across manufacturing and supply chain — none have reached production

- No unified AI strategy or enterprise platform to convert POCs into operational capability

- Digital-first operations remain an aspiration, not a delivered outcome

- Sadara's AI maturity sits at Level 1–2 (Ad-hoc/Experimenting) against an industry moving to Level 4–5 (Managed/Optimized)

- Sadara operates under a complex and growing set of regulatory obligations such as IEC 62443 for OT cybersecurity, RC14001 for Responsible Care chemical safety with NCA, NDMO, SDAIA alongside — none of which are fully addressed by the current technology architecture

### Functional Shortcomings

Manufacturing and Plant Operations

- 26 manufacturing units with manual scheduling, calendar-based maintenance

- Unplanned downtime costs $800K–$1.2M per day per unit

- Process optimization relies on offline Aspen models (disconnected from live DCS)

- Operators rely on alarms and tribal knowledge — no predictive intelligence

Supply Chain & Logistics

- Distribution across Saudi Arabia and 30+ export markets is spreadsheet-driven

- Route optimization manual; inventory decisions weekly, not real-time

- Goods return processing takes 15–20 business days

- Warehouse allocation is first-come-first-served, not optimized

Commercial & Trading

- Chemical pricing relies on FPS engine with manual market adjustments

- ETRM processes trades but provides zero predictive intelligence

- Sales teams lack AI-powered customer insights

- Contract negotiations based on historical pricing only

Finance & Accounting

- Monthly financial close takes 10+ business days

- Reconciliation across 6 banking relationships is manual

- Budget variance analysis is backward-looking only

- Cash flow forecasting doesn't account for commodity price volatility in real-time

Human Resources & Safety

- Workforce planning for 4,200 employees + 12,000 contractors is entirely manual

- Turnaround staffing requires 3–4 months planning lead time

- Safety incident prediction is reactive (post-incident investigation only)

- Fatigue management and crew optimization are manual processes

IT Operations & Cybersecurity

- 4,200+ support tickets/month with 40% repeat issues — no deflection

- Infrastructure monitoring is reactive, not predictive

- OT cybersecurity relies on perimeter defenses, limited AI threat detection

- Shadow IT creates unmonitored attack surfaces (60+ ungoverned tools)

### Technical Debt

| SYSTEM CLUSTER | CURRENT SYSTEMS | KEY PAIN POINTS | TECH DEBT TYPE |
| --- | --- | --- | --- |
| Trading & Pricing | ETRM, FPS Pricing Engine, DistSys, Crude Oil/Gas Trade | Monolithic ETRM, no AI pricing, manual reconciliation | Architecture / Data Silo |
| CRM & Sales | Salesforce CRM (Sales + Marketing) — 2 instances | Dual instances, data duplication, no AI pipeline | Data Duplication / Shadow CRM |
| BPM & Workflow | PEGA BPM, custom workflow tools | Expensive licenses, limited SAP integration, no intelligent automation | License Debt / Integration Gap |
| HR & Workforce | Workday, Kronos/UKG, separate planning tools | Not integrated with plant scheduling; no AI-driven planning | Integration Gap |
| ERP & Finance | SAP ECC 6.0, SAP Ariba, CorpTax, Blackline | ECC End-of-Life, 340+ ABAP, 10-day close | End-of-Life / Custom Code Debt |
| OT & Process Control | DCS (Honeywell/Yokogawa), PI Suite, SCADA, SIS | 85K tags, no AI/ML layer, DCS data stays in control room | OT/IT Disconnect |
| Process Engineering | Aspen Suite (HYSYS, DMC+, Advisor), CEMS, MD Pro | Offline models, no closed-loop optimization | Simulation-Operations Gap |
| Planning & Projects | Primavera P6, Track, project management tools | Calendar-based maintenance; no AI turnaround planning | Process Maturity Gap |
| IT Service & Analytics | ServiceNow, Power BI, Tableau, Cognos, Alteryx, Palantir | Overlapping tools, no AI, backward-looking reporting | Tool Sprawl / Analytics Debt |
| Shadow IT (60+ tools) | Custom DBs, Access tools, Excel macros, dept tools | Critical processes on unsupported tools; data quality unknown | Shadow IT / Governance |

## Impact Summary

| $50M+ IT budget locked in maintenance | $1.2M/day Downtime cost per unit | 120+ Fragmented applications | 85,000+ OT tags not reaching AI | 10+ days Monthly financial close | 0 AI models in production |
| --- | --- | --- | --- | --- | --- |

# Our Proposed Solution

## Enterprise AI Operating System (EOS) – Solution Overview

Sadara’s transformation requires more than incremental improvements — it requires a unified operating model that connects data, intelligence, and execution across the enterprise.

Wipro proposes the implementation of an Enterprise AI Operating System (EOS) to transform Sadara from a fragmented, reactive organization into a unified, AI-driven enterprise.

The EOS is designed as a scalable, enterprise-wide platform that connects data, intelligence, and execution across all business functions. Rather than deploying isolated use cases, Wipro’s approach delivers a single, integrated operating model that enables real-time decision-making, automation, and continuous optimization.

At its core, the EOS addresses Sadara’s key challenges — fragmented systems, disconnected data, and limited AI adoption — by establishing a unified foundation for enterprise intelligence.

Three Core Pillars of the EOS

  - Unified Data Fabric
A governed, real-time data foundation that integrates enterprise applications (SAP, Salesforce, Workday, ETRM) with operational technology systems (DCS, PI, SCADA). This eliminates data silos and creates a single source of truth, enabling consistent and reliable data across the organization.

  - Domain AI Agents
A portfolio of AI agents across Manufacturing, Supply Chain, Commercial, Finance, HR & Safety, and IT Operations. These agents leverage machine learning and real-time data to provide predictive insights, automate workflows, and support decision-making at both operational and executive levels.

  - Intelligent Rationalization
A structured approach to reducing application sprawl and technical debt. By consolidating overlapping systems and modernizing legacy platforms, Sadara can shift IT investment from maintenance to innovation while improving system performance and governance.

How the EOS Delivers Value

The EOS enables Sadara to transition from manual, experience-based operations to an AI-enabled operating model that is proactive, data-driven, and scalable.

Key capabilities include:

- Real-time integration of OT and enterprise data

- Predictive maintenance and process optimization

- AI-driven supply chain and commercial decision-making

- Automated financial processes and improved forecasting

- Enhanced workforce planning and safety monitoring

- Intelligent IT operations and cybersecurity

Business Outcomes

Through the EOS, Sadara can achieve measurable and sustainable improvements, including:

- Up to 40% reduction in unplanned downtime

- 3–5 day financial close

- 15–20% inventory optimization

- 60% reduction in IT service tickets

- Improved safety, compliance, and operational resilience

A Unified Enterprise Transformation

Wipro’s EOS is not a collection of disconnected tools or pilots — it is a unified transformation framework that aligns technology, data, and business processes into a single operating model.

By combining Wipro’s ai360 platform, industry accelerators, and deep domain expertise, Sadara is enabled to scale AI across the enterprise and achieve long-term competitive advantage.

This approach is demonstrated through a live use case, showcasing how domain AI agents interact with enterprise and OT data to deliver real-time decision support.

## Proposed Solution Architecture

The EOS is enabled through a layered, enterprise architecture designed to securely integrate OT and IT systems while supporting real-time AI-driven decision-making.

### Architecture Philosophy

Sadara's Enterprise AI Operating System is designed on a layered, domain-agnostic architecture that separates concerns across data acquisition, governance, intelligence, and action.

The architecture follows the industry-standard Medallion pattern for data refinement, an industry compliant OT/IT security boundary for plant data, and a centralized integration fabric for agent-to-enterprise connectivity.

Every layer is designed to operate within the Kingdom of Saudi Arabia, fully compliant with Saudi NCA Essential Cybersecurity Controls, NDMO Data Governance Framework, SDAIA AI Ethics requirements, and Saudi PDPL data protection law.

The architecture is vendor-agnostic at the platform layer — technology selections are made based on Sadara's existing investments, integration depth, and total cost of ownership over a five-year horizon.

### Layer 0 – Hybrid Infrastructure, Cybersecurity & Business Continuity

Sadara's EOS operates on a hybrid infrastructure model — on-premises computed at Jubail, edge computed at each of 26 manufacturing units, and sovereign cloud within the Kingdom. This is the target architecture, not a transitional state — no single deployment model satisfies Sadara's combination of latency, data residency, and operational continuity requirements.

The primary compute layer — Lakehouse, ingestion, AI agents, and ESB — runs on Google Cloud Platform within Saudi Arabia, keeping all sensitive data within the Kingdom. The environment is high-availability with no single point of failure, petabyte-scale storage for 85,000+ OT tags and enterprise data, and QoS rules prioritizing safety-critical data flows.

SAP BTP Saudi Arabia region hosts the integration services. Saudi cloud regions support burst model training and will use encrypted dedicated links.

AI Inference based Edge hardware will be deployed across all manufacturing units to capture the real-time insights using Edge inference where the latency is under 500 milliseconds and data doesn’t leave the facility for analysis.

Zero Trust - No user, system, agent, or edge device is trusted by default. Every access request is authenticated, authorized to minimum permissions, and logged. Short-lived scoped tokens replace long-lived credentials. Micro-segmentation prevents lateral movement across all zones.

OT Security All OT-to-IT flows are outbound only — enforced at the firewall, not by policy alone. No IT or cloud system can initiate a connection into the OT network. Edge devices at plant units do not accept inbound connections — model updates are initiated by the device outbound.

Identity and Access Management Centralized IAM governs all identities. Role-based access defined at data domain and action level. Privileged access uses just-in-time provisioning, mandatory MFA, and full session recording. No standing privileged access in production.

The EOS is designed for operational continuity under infrastructure failure, cyber incident, and regional disruption scenarios. Recovery objectives are defined per component based on business criticality — ranging from immediate autonomous recovery at the edge to four-hour RTO for the central Lakehouse. DR runbooks are tested quarterly through tabletop exercises and biannually through live failover. AI-specific incident procedures — model rollback, agent suspension, and adversarial input response — are tested at minimum twice per year.

### Layer 1 – Source Systems

Source systems are classified into three clusters based on data characteristics, connectivity patterns, and network security boundaries:

- Enterprise Applications Core business systems forming the transactional backbone of Sadara's operations. This cluster includes SAP ECC 6.0 (planned S/4HANA migration), SAP Ariba, SAP BW, SAP BTP, Salesforce CRM (dual instances), Workday HCM, and PEGA BPM. These systems are the primary sources of structured transactional data — financial records, procurement transactions, customer interactions, workforce data, and business process states.

- IT Systems and Analytics Operational and analytical systems supporting Sadara's IT and commercial functions. This cluster includes ServiceNow ITSM, ETRM (Energy Trading and Risk Management), Microsoft 365, Power BI, CorpTax, Blackline, and standalone analytical tools. These systems generate semi-structured and unstructured data — tickets, contracts, reports, emails.

- OT and Plant Floor Systems Operational technology systems across Sadara's 26 manufacturing units in Jubail Industrial City. This cluster includes DCS systems (Honeywell Experion, Yokogawa CENTUM), SCADA infrastructure with 85,000+ instrument tags, Safety Instrumented Systems (SIS), and process engineering tools including the Aspen Suite (HYSYS, DMC+, Advisor) and OSIsoft PI Historian. These systems generate high-frequency time-series data — process variables, equipment states, quality measurements, and safety signals — that are currently confined to the OT network and unavailable for enterprise AI decision-making.

### Layer 2 – Connectivity & Integration

Connectivity strategy is differentiated by source systems, reflecting the protocol diversity across Sadara's application landscape.

Enterprise Application Connectivity

- SAP systems are connected via native SAP protocols — Remote Function Calls (RFCs) and Business Application Programming Interfaces (BAPIs) for SAP ECC transactional data, OData REST APIs for SAP BTP and planned S/4HANA integration, and IDocs for bulk data exchange and event-driven messaging.

- This approach requires no middleware translation and ensures full compatibility with the planned S/4HANA migration — the integration layer remains unchanged when the ERP backend transitions.

- Salesforce CRM is connected via Salesforce REST API with OAuth 2.0 authentication.

- Workday HCM is connected via Workday REST API and SOAP-based Web Services with OAuth 2.0.

- PEGA BPM is connected via PEGA REST APIs and webhook-based event notifications for process state changes.

IT System Connectivity

- ServiceNow is connected via ServiceNow REST API with OAuth 2.0 authentication enabling bidirectional ticket data flow and AI-driven resolution write-back.

- ETRM is connected via REST API or messaging queue depending on the ETRM vendor's integration capabilities.

- Microsoft 365 is connected via Microsoft Graph API with OAuth 2.0, enabling document ingestion, email metadata, and collaboration data for unstructured AI use cases.

OT System Connectivity — Secure DMZ Architecture

- OT system connectivity requires a dedicated security-compliant Demilitarized Zone architecture, distinct from enterprise application connectivity, due to the IEC 62443 industrial cybersecurity standard.

- Sadara's existing OSIsoft PI Historian consolidates all 85,000+ instrument tags from DCS, SCADA, SIS, and field instrumentation systems via native OPC-UA and proprietary PI interface protocols. This existing investment is the foundation of the OT integration strategy — the ingestion layer does not connect to DCS systems directly, and no changes are made to the OT control layer.

- A PI Web API server is deployed in a dedicated DMZ — a network segment isolated from both the OT network and the IT network by two independent firewall layers. This server runs AVEVA PI Web API, exposing a read-only HTTPS endpoint that serves PI Historian data to the IT network without exposing the OT network itself.  No inbound connection from the IT network reaches the OT network at any point.

- The ingestion platform connects to the DMZ PI Web API endpoint via its native REST connector, using certificate-based authentication over HTTPS. This enables both near-real-time streaming of current tag values — with configurable polling intervals down to five seconds for critical process variables — and historical backfill for model training across the full PI archive.

- This architecture is fully compliant with IEC 62443 industrial cybersecurity standards, Sadara's Purdue model network segmentation, and Saudi NCA Essential Cybersecurity Controls. The OT control layer remains operationally independent — plant operations are unaffected by any IT or AI system event.

### Layer 3 – Data Ingestion, Cleansing and Governance

The ingestion and governance layer is the trust foundation of the EOS. All data entering the Lakehouse passes through this layer — no source system connects directly to the Lakehouse without traversing governance controls.

Ingestion

- The ingestion platform supports batch, micro-batch, and streaming ingestion patterns simultaneously.

- Enterprise application data from SAP and Salesforce is ingested on scheduled batch and micro-batch cycles aligned to business process cadence — financial data on daily close cycles, inventory data every fifteen minutes, and customer data hourly.

- OT sensor data from PI Historian is ingested in near-real-time via continuous polling of the DMZ PI Web API endpoint.

- Event-driven data from PEGA and ServiceNow is ingested via webhook triggers on process state changes.

Field-Level Cleansing

- At the point of ingestion, field-level data quality operations are applied before data lands in the Lakehouse.

- These operations include null detection and handling, data type validation and coercion, format standardisation — all timestamps normalised to UTC, all numeric units standardised to SI — duplicate detection within a single source, and referential integrity validation against known master data domains.

- These operations are applied inline within ingestion pipelines and do not require a separate processing step.

PII Masking and Data Minimisation

- All personally identifiable information is identified and handled at the ingestion layer, prior to landing in the Lakehouse.

- Employee names, national ID numbers, contact details, salary information, and any other data classified as personal under Saudi PDPL are masked, tokenised, or redacted according to data classification policy.

- Data minimisation principles are enforced — only fields necessary for the defined AI use case are ingested; unnecessary personal data is not collected. This approach ensures PDPL compliance is architectural rather than procedural.

Master Data Management

- The governance layer maintains a master data registry covering key business entities — equipment, material, customer, vendor, employee, and cost centre.

- Source system records are matched, merged, and consolidated into golden records.

- This resolves the current fragmentation where the same customer exists differently in Salesforce Sales, Salesforce Marketing, and SAP SD — the golden record provides a single, authoritative reference used consistently across all downstream AI models and analytics.

Data Lineage and Classification

- Every data asset in the Lakehouse carries full lineage metadata — source system, ingestion timestamp, transformation applied, quality score, data classification level (Public, Internal, Confidential, Restricted), and PDPL personal data flag.

- Lineage is maintained end-to-end from source field to Gold feature — enabling audit-testable evidence of data provenance for regulatory compliance and AI model explainability.

### Layer 4 – Unified Data Lakehouse

The unified data Lakehouse is the single source of truth for all enterprise and OT data, supporting structured transactional data, high-frequency time-series sensor data, unstructured documents and logs, and AI model artifacts — all within one governed, quarriable platform. The Lakehouse operates entirely within the Kingdom of Saudi Arabia (GCP), satisfying NDMO data residency requirements.

Data within the Lakehouse is organised in three refinement layers following the industry-standard Medallion architecture:

Bronze Layer – Source Conformed Layer

- Bronze tables contain data exactly as received from source systems after field-level cleansing and PII masking applied at ingestion.

- Bronze is append-only — no records are deleted or modified.

- This preserves the full audit trail and enables reprocessing of downstream layers if business logic changes.

- Bronze tables are partitioned by source system and ingestion date for efficient incremental processing.

Silver — Cleansed and Conformed Layer

- Silver tables are produced by the Lakehouse transformation engine from Bronze sources.

- At this layer, cross-source joins are performed — OT sensor readings from PI Historian are joined with SAP equipment master data to produce contextualised process records; SAP maintenance orders are joined with reliability data to produce equipment maintenance history; Workday shift records are joined with plant unit assignments to produce workforce context.

- Business rule validation is applied — values are checked against physical and business constraints, anomalies are flagged, and data quality scores are assigned.

- Time-series aggregations are computed — rolling averages, standard deviations, trend indicators, and change detection flags for sensor data streams.

- Silver represents a single, trusted, conformed view of each business entity and process.

Gold — Feature-Rich, AI-Ready Layer

- Gold tables are purpose-built for specific AI agent domains.

- They are produced by joining and aggregating Silver tables across multiple domains, computing business-specific features, and applying ML model inference to produce predictive scores and recommended actions.

- A Gold table for predictive maintenance, for example, joins equipment master, sensor aggregates, maintenance history, spare parts availability, and workforce shift data — then applies a trained failure prediction model to produce a per-equipment failure probability, recommended action, and urgency score.

- AI agents read exclusively from Gold tables — they do not query Silver or Bronze directly. This ensures agent response latency is minimised and agent logic is decoupled from raw data complexity.

The Lakehouse also maintains a Feature Store — a curated registry of reusable ML features computed from Silver data, versioned and shareable across multiple AI models. This prevents feature precomputation and ensures consistency when the same feature is used by different agents or models.

A Model Registry — integrated with the MLOps pipeline — tracks every AI model deployed against Gold data: training dataset version, performance metrics, approval status, deployment date, drift monitoring thresholds, and retirement lineage. No model enters production without passing formal review gates covering accuracy, bias testing, security validation, and operational readiness.

### Layer 5 – Agentic AI Platform

The Agentic AI Platform is the intelligence layer of the EOS. It consumes AI-ready Gold data from the Lakehouse and operationalises it through domain-specific AI agents that reason, plan, and act across Sadara's business domains.

Domain AI Agents

Six domain AI agents are deployed, each purpose-built for a specific business domain:

- The Manufacturing and Operations Agent monitors equipment health across all 26 units, detects process anomalies in near-real-time, generates predictive maintenance recommendations, optimises production scheduling, and supports quality prediction — preventing off-spec production before it occurs.

- The Supply Chain and Logistics Agent performs demand-supply matching, optimises distribution routes across Saudi Arabia and 30+ export markets, accelerates goods return processing, and provides end-to-end supply chain visibility from plant gate to customer delivery.

- The Commercial and Trading Agent generates AI-augmented pricing recommendations based on market signals, inventory levels, and competitive intelligence, identifies trading opportunities within the ETRM landscape, and supports customer churn prediction and retention strategies.

- The Finance and Compliance Agent accelerates financial close through automated reconciliation, performs continuous controls monitoring, generates real-time cash flow forecasts with commodity-linked scenarios, and supports transfer pricing compliance for the JV structure.

- The HR, Safety and Workforce Agent performs AI-driven workforce demand forecasting for turnarounds and maintenance windows, predicts safety incidents from leading indicator patterns, optimises shift scheduling and fatigue management, and identifies skills gaps with training path recommendations.

- The IT Operations and Cybersecurity Agent deflects L1 service desk tickets through AI self-service, performs predictive infrastructure monitoring, detects OT cybersecurity threats aligned with IEC 62443, and discovers shadow IT risk across Sadara's application landscape.

Agent Architecture: Each agent is implemented as an agentic workflow — not a single model call, but an orchestrated sequence of reasoning steps, tool invocations, data lookups, and decision points. Agents are capable of multi-step planning: decomposing a complex business question into sub-tasks, calling appropriate tools and data sources, synthesising results, and producing a structured recommendation with supporting evidence. Agents operate with defined tool sets — they can query the Lakehouse, invoke the ESB to trigger enterprise system actions, call external APIs where approved, and escalate to human approvers when uncertainty or risk thresholds are exceeded.

Human Approval Engine: All agent-initiated actions are classified under a three-tier risk framework before execution:

Tier 1 — Safety-Critical actions, including any recommendation influencing process control, maintenance scheduling, or safety system state, require full human review and explicit sign-off before the ESB routes the action to the target system. The agent presents its recommendation with full reasoning, confidence score, and supporting evidence. The human approver accepts, modifies, or rejects. All decisions are logged with the approver identity, timestamp, and rationale.

Tier 2 — Financial and Regulatory actions, including journal postings, procurement commitments, and compliance-affecting decisions, require human approval from a designated authority level appropriate to the transaction value and risk.

Tier 3 — Productivity and Advisory actions, including ticket routing, report generation, and non-binding recommendations, are executed automatically with logging. Users retain the ability to override any Tier 3 action without penalty.

Model Governance and MLOps All AI models powering agent workflows are managed through a centralised MLOps pipeline covering the full model lifecycle — data preparation, training, evaluation, bias testing, security review, deployment, monitoring, retraining, and retirement. Models in production are monitored continuously for performance degradation and data drift. Automated alerts trigger retraining workflows when drift exceeds defined thresholds. No model runs in production for more than 90 days without formal performance revalidation. Every model is registered in the Model Registry with full lineage documentation — ensuring auditability and enabling rapid rollback if a model produces consequential errors.

AI Security Agent inference is secured through role-based access control — agents access only the Gold data domains relevant to their function. All agent-to-ESB communications are encrypted in transit. Agent actions are logged in a tamper-proof audit trail. A kill-switch mechanism is implemented for every Tier 1 and Tier 2 agent — operators can suspend agent recommendations instantly without impacting underlying system operations.

### Layer 6 – Enterprise Service Bus

Rather than allowing AI agents to connect directly to enterprise systems — which would result in unmanageable point-to-point integrations, dispersed credentials, and fragmented audit trails — a centralised Enterprise Service Bus (ESB) layer is introduced as the single integration fabric between the Agentic AI Platform and all enterprise systems.

The ESB serves five critical functions in the EOS architecture:

- Protocol Translation

- Enterprise systems across SADARS's landscape speak materially different integration protocols.

- SAP ECC communicates via BAPIs, IDocs, and RFCs. SAP S/4HANA exposes OData REST APIs. Workday uses SOAP-based web services.

- ETRM systems use proprietary messaging formats.

- The ESB translates all agent-generated REST/JSON instructions into the native protocol required by each target system — insulating agents from protocol complexity and ensuring that system upgrades, including the planned SAP ECC to S/4HANA migration, require only ESB configuration changes rather than agent re-engineering.

- Centralised Security and Access Control

- All enterprise system credentials are stored in a centralised secrets vault managed by the ESB.

- No AI agent holds direct credentials for any enterprise system.

- Agents authenticate to the ESB using short-lived tokens with scoped permissions — an agent can only invoke the specific ESB endpoints authorised for its domain.

- This eliminates credential sprawl, enables immediate access revocation, and provides a single security perimeter for all enterprise system interactions.

- Approval Workflow Routing

- The ESB is the enforcement point for the human approval engine.

- Every agent action passes through the ESB before reaching a target system.

- The ESB evaluates the action against the risk classification framework — routing Tier 1 and Tier 2 actions to designated human approvers via notification, holding execution until approval is received, and releasing the action to the target system only upon explicit authorisation.

- Rejected actions are logged with rejection reason and fed back to the agent for re-evaluation.

- Audit Trail and Compliance Logging

- Every action processed by the ESB is logged in a structured, tamper-proof audit record capturing: agent identity, action type, target system, payload summary, approval status, approver identity where applicable, execution timestamp, and outcome.

- This audit trail satisfies SOX-compatible logging requirements for financial AI actions, Saudi NCA audit requirements, and NDMO governance obligations.

- Audit logs are retained for the period required by applicable regulations and are quarriable for compliance reporting.

- Throttling and Reliability

- The ESB manages message queuing, rate limiting, and retry logic — ensuring that concurrent agent activity does not exceed enterprise system API limits or create performance degradation.

- Failed actions are held in a dead letter queue with alerting, preventing silent data loss.

- The ESB provides guaranteed message delivery — if a target system is temporarily unavailable, actions are queued and executed on recovery without agent re-invocation.

The recommended ESB platform for Sadara is SAP BTP Integration Suite — already present in Sadara's technology landscape under limited adoption and planned for expansion. SAP BTP Integration Suite provides native, certified connectivity to the full SAP ecosystem without custom development, pre-built adapters for Salesforce, Workday, and ServiceNow, full S/4HANA compatibility ensuring continuity through the ERP migration, and deployment options within the SAP Saudi Arabia data centre region satisfying data residency requirements.

### Layer 7 – Experience Layer

The experience layer is where the EOS becomes visible to Sadara's 4,200 employees and 12,000 contractors. It ensures AI is accessible, intuitive, and trustworthy across every user segment — from plant operators to board members.

- Management Dashboards — Real-Time Intelligence Live operational dashboards replacing backward-looking reports. Every KPI links to the underlying AI recommendation that influenced it — giving managers full visibility of AI contribution to operational performance.

- Approval Interface — All Roles Structured approval requests present recommendation, reasoning chain, confidence score, risk tier, and alternatives — actionable from web or mobile with Teams and email notification. Override patterns feed model improvement — never used to evaluate human performance.

- Bilingual by Design All interfaces built in Arabic and English from the start — not translated as an afterthought. AI recommendations, alerts, and voice commands generated natively in the user's preferred language with full right-to-left layout support.

- Adoption Measurement Tracks decision quality metrics — recommendation acceptance rates, time saved, user NPS, and override trends — not login counts. Real-time adoption heatmap across all 26 units and departments enables targeted change management where adoption is lagging.

## EOS Platform Pillars

The EOS is powered by three integrated platform pillars — each addressing a distinct phase of Sadara's transformation. Together they form a unified, production-ready foundation built on WIPRO's industry-proven assets, two-decade technology partnerships, and field-validated accelerators purpose-built for complex industrial environments.

| Pillar 1 | Pillar 2 | Pillar 3 |
| --- | --- | --- |
| Intelligent Rationalization | Smart & Safe Industrial AI Platform | Wipro ai360 Intelligence: Unified Data & Agentic AI |
| Clean the house | Protect the plant | Power the enterprise |

Pillar 1 — Intelligent Rationalization

Sadara's 120+ application landscape consumes 65% of the IT budget in maintenance — leaving only 35% for innovation. Before any AI capability is deployed, the application estate must be rationalised. Intelligent Rationalization is WIPRO's structured approach to converting a fragmented application landscape into a governed, right-sized core — freeing budget, reducing risk, and creating the clean foundation on which the EOS is built.

- Live Application Inventory A complete, automated discovery of Sadara's 120+ application landscape — capturing usage patterns, integration dependencies, licensing costs, support burden, and business criticality. The inventory is not a spreadsheet exercise — it is a live, continuously updated registry that becomes the single source of truth for all rationalization decisions throughout the programme.

- Tech Debt Scoring Every application is scored across five dimensions.

  - business value,

  - technical health,

  - integration complexity,

  - compliance risk, and

  - total cost of ownership.

Scoring is data-driven and transparent — business owners see exactly why an application is recommended for retirement or consolidation, not just that it is. The tech debt score becomes the objective basis for prioritisation decisions, removing politics from what is inherently a political process.

- Disposition Framework — Keep / Migrate / Retire / Consolidate Each application receives a disposition recommendation backed by the tech debt score and business case. Applications are classified into four categories: Keep and integrate into the EOS platform, migrate to a modern equivalent or SAP standard functionality, retire with business process absorbed by an AI agent, or consolidate where duplicate applications serve the same function. The target — reducing 120+ applications to 40–60 core systems within 36 months — is achieved progressively across delivery waves, not as a front-loaded gate.

Pillar 2 – Wipro Smart iSAFE

Wipro Smart iSAFE is a field-proven industrial AI platform purpose-built for chemical, energy, and manufacturing environments. For Sadara's 26 manufacturing units — where AI decisions can influence safety-critical operations — Smart iSAFE provides the production-ready industrial AI foundation that generic AI platforms cannot match. It is not a proof of concept. It is deployed, validated, and operational in comparable industrial environments.

- Industrial Data Ingestion Smart i Safe ingests plant-floor data from DCS, SCADA, PI Historian, and field instrumentation systems — the raw operational signals that conventional enterprise platforms cannot consume natively. For Sadara, this covers 85,000+ instrument tags across 26 units, providing the real-time process intelligence layer that sits between the OT environment and the enterprise AI platform.

- Proactive Safety Incident Detection When anomalous conditions are detected — equipment behaviour outside safe operating parameters, environmental sensor thresholds, or access control violations — Smart i Safe proactively notifies relevant workers and supervisors before an incident escalates. Notifications are contextual, role-specific, and delivered through the appropriate channel for the urgency level. The system moves Sadara from reactive incident investigation to predictive safety intervention.

- Restricted Zone Monitoring Smart i Safe monitors access to restricted zones in real time — detecting unauthorised entry events via IoT sensors and RFID, correlating with active Permit to Work status, and triggering immediate alerts to shift supervisors when violations occur. Worker identity is resolved via RFID exclusively — no facial recognition — maintaining privacy compliance under Saudi PDPL.

- Computer Vision — PPE, Fatigue, and Behaviour Real-time computer vision models run at the edge — on NVIDIA Jetson devices deployed at each manufacturing unit — analysing live CCTV feeds for PPE compliance (helmet, vest, gloves), fatigue indicators, and unsafe worker behaviour. Models run locally at 25–30 frames per second with sub-500 millisecond alert latency. Raw video never leaves the plant unit — only structured inference results are transmitted, preserving privacy and OT network integrity. Detections automatically trigger the safety incident workflow — alerting supervisors, creating records in SAP EHS, and logging to the Lakehouse for audit and model improvement.

Pillar 3 – Wipro ai360 Intelligence

Wipro ai360 Intelligence is the enterprise AI core of the EOS — the unified data and agentic AI platform that transforms Sadara's fragmented data landscape into a single source of truth and deploys domain-specific AI agents that reason, decide, and act across every business function. It is built on Wipro's two flagship technology partnerships — Informatica for data governance and Databricks for unified analytics and AI — both representing over two decades of joint delivery at enterprise scale.

- Informatica IDMC — Data Governance Foundation Wipro's two-decade partnership with Informatica underpins the data governance layer of the EOS. Informatica Intelligent Data Management Cloud (IDMC) connects to all source systems — SAP via native RFC/BAPI/OData connectors, Salesforce and Workday via REST APIs, and OSIsoft PI Historian via PI Web API through the DMZ — applying field-level cleansing, PII masking, master data management, and end-to-end lineage tracking before data lands in the Lakehouse. Every piece of data entering the platform is governed, classified, and traceable from source to AI decision — satisfying Saudi PDPL, NDMO, and audit requirements by design.

- Databricks — A Unified Lakehouse and AI Platform. Wipro's partnership with Databricks powers the unified data Lakehouse and agentic AI platform at the core of the EOS. All data — structured SAP transactions, OT sensor streams, HR records, commercial data, and unstructured documents — lands in a single governed Delta Lake environment following the Medallion architecture: Bronze for raw ingestion, Silver for cleansed and conformed data, and Gold for feature-rich, AI-ready domain datasets. Databricks Delta Live Tables manages the Bronze-to-Gold pipeline — declarative, monitored, and automatically recovering. Unity Catalog enforces access control, data classification, and lineage across all layers.

- ML Models and Feature Store Domain-specific ML models — predictive maintenance, demand forecasting, quality prediction, financial anomaly detection, workforce planning — are trained on Gold datasets, managed through MLflow in the Model Registry, and governed through the full MLOps lifecycle. A centralized Feature Store provides versioned, reusable features shared across models — preventing inconsistency between training and production and accelerating new use case development as the CoE matures.

- Agentic AI (Six Domain Agents) Databricks Mosaic AI powers six domain-specific agentic workflows — Manufacturing and Operations, Supply Chain and Logistics, Commercial and Trading, Finance and Compliance, HR Safety and Workforce, and IT Operations and Cybersecurity. Each agent is a multi-step orchestrated workflow — not a single model call — capable of decomposing complex business questions, querying the Lakehouse, invoking ML models, seeking human approval, and executing approved actions through the ESB.

# Functional Domain AI solutions

Wipro’s EOS is operationalized through 21 domain-specific AI agents across six business functions. Each agent is designed to address a specific operational challenge at Sadara, delivering measurable business outcomes through automation, prediction, and real-time decision support.

These agents are not standalone tools — they are integrated into Sadara’s enterprise systems and workflows, enabling end-to-end execution from insight to action.

These AI agents are deployed in a phased manner aligned to business priority and data readiness, with impact measured through defined KPIs and independently verified outcomes.

Manufacturing & Plant Operations (4 Agents)

| # | Agent | What It Solves | Business Impact |
| --- | --- | --- | --- |
| 1 | PPE & Restricted Zone Compliance | Workers entering restricted zones without PPE detected in real time via computer vision and IoT sensors Shift supervisors alerted instantly, incident logged automatically in SAP EHS, enables proactive prevention, reducing incident risk and response time. | Reduces safety incidents through real-time detection and automated escalation, improving compliance and lowering incident response time across all units. |
| 2 | Predictive Maintenance | Calendar-based maintenance is replaced with condition-based intervention. Equipment failure probability scored daily from PI Historian sensor data, work orders raised in SAP PM before breakdown occurs, eliminating $800K–1.2M/day unplanned downtime per unit. | Reduces unplanned downtime by up to 40%, avoiding $800K–$1.2M per day per unit and improving asset reliability and maintenance efficiency. |
| 3 | Process Optimization | Offline Aspen simulation models disconnected from live DCS. The Agent ingests real-time process variables and recommends yield adjustments to operators, connecting simulation intelligence to live operations for the first time. | Increases yield and throughput by 2–5% by connecting simulation models to live operations, enabling real-time process adjustments. |
| 4 | Operator Decision Support | Operators are overwhelmed by alarms and tribal knowledge. The Agent contextualizes alerts with equipment history, process context, and recommended action, reducing alarm fatigue and capturing expert knowledge before it walks out the door. | Reduces alarm fatigue and decision time by up to 30%, improving operational consistency and preserving critical institutional knowledge. |

Supply Chain & Logistics (4 Agents)

| # | Agent | What It Solves | Business Impact |
| --- | --- | --- | --- |
| 5 | Demand Sensing | Weekly Excel-based demand planning across 30+ export markets replaced with continuous AI forecasting on SAP sales history, market signals, and customer order patterns, enabling real-time supply decisions. | Improves forecast accuracy by 20–30%, enabling faster response to market changes and reducing stockouts and excess inventory. |
| 6 | Goods Return Automation | Goods return processing taking 15–20 business days due to manual classification and routing. This Agent classifies return reason, validates against contract, routes automatically, and updates SAP SD, reducing cycle to 3–5 days. | Reduces return processing cycle time by 70–80%, from 15–20 days to 3–5 days, improving customer satisfaction and cash recovery. |
| 7 | Route Optimization | Distribution routes planned manually on spreadsheets. The Agent optimizes routes across Saudi Arabia and export markets dynamically, accounting for inventory levels, delivery windows, and logistics costs, targeting 8–12% cost reduction. | Lowers logistics costs by 8–12% through dynamic route planning, improving delivery efficiency across domestic and export markets. |
| 8 | Warehouse Optimization | First-come-first-served warehouse allocation creating inefficiency and excess holding costs. Here the Agent recommends optimal allocation based on demand forecast, expiry, and customer priority, reducing inventory holding costs 15–20%. | Reduces inventory holding costs by 15–20% while improving inventory turnover and warehouse utilization efficiency. |

Commercial & Trading (3 Agents)

| # | Agent | What It Solves | Business Impact |
| --- | --- | --- | --- |
| 9 | Price Recommendation | Chemical pricing set manually against FPS engine with no real-time market intelligence — agent synthesizes ETRM positions, Salesforce customer records, competitor price signals, and commodity indices to recommend optimal pricing per product and market. | Increases margin by 2–4% through data-driven pricing aligned to market signals, customer behavior, and commodity trends. |
| 10 | Customer Intelligence | No unified customer view across dual Salesforce instances — agent builds customer 360 from consolidated CRM data, scores churn risk, identifies upsell opportunity, and surfaces next best action for sales teams. | Improves customer retention and upsell conversion by 10–15% through unified customer insights and targeted sales actions. |
| 11 | Contract Analysis | Contract review and risk flagging done manually by commercial and legal teams — agent reads contract documents, identifies non-standard clauses, flags pricing risk, and benchmarks against historical contracts. | Reduces contract review time by 60–70% while improving risk detection and compliance across commercial agreements. |

Finance & Accounting (3 Agents)

| # | Agent | What It Solves | Business Impact |
| --- | --- | --- | --- |
| 12 | Intelligent Financial Close | Monthly close taking 10+ business days due to manual sequencing, approvals, and inter-system dependencies — agent orchestrates close tasks, auto-posts routine journals, chases open items, and targets 3–5 day close. | Reduces financial close cycle from 10+ days to 3–5 days, improving reporting timeliness and financial visibility. |
| 13 | Automated Reconciliation | Reconciliation across 6 banking relationships and intercompany JV transactions done entirely manually — agent matches transactions, auto-posts matched items, flags exceptions only, targeting 90%+ straight-through reconciliation. | Achieves 90%+ straight-through reconciliation, reducing manual effort and improving accuracy across banking and intercompany transactions. |
| 14 | Cash Flow Forecasting | Cash flow forecasts built on static assumptions with no commodity price linkage — agent models real-time cash position against open receivables, payables, ETRM commodity exposure, and FX, delivering rolling 30/60/90-day forecasts. | Improves forecast accuracy by 25–40%, enabling better liquidity management and risk mitigation tied to commodity and FX exposure. |

Human Resources & Safety (3 Agents)

| # | Agent | What It Solves | Business Impact |
| --- | --- | --- | --- |
| 15 | Predictive Safety Analytics | Safety incidents investigated after they occur with no early warning system — Smart i Safe agent analyses leading indicators from sensor data, near-miss logs, fatigue patterns, and permit history to predict and prevent incidents before they happen. | Reduces safety incidents by up to 20–30% through early detection of risk patterns and proactive intervention. |
| 16 | Fatigue and Staffing AI | Turnaround staffing planned manually over 3–4 months with no fatigue management — agent models shift history, certifications, fatigue risk scores, and contractor availability to optimize crew assignments and flag high-risk staffing gaps. | Reduces staffing-related risk and improves workforce efficiency by optimizing crew allocation and minimizing fatigue-related incidents. |
| 17 | Skills Gap and Training | Workforce capability assessment done manually with no AI-driven gap analysis — agent maps current employee skills against AI-enabled role requirements, recommends training paths, and flags critical capability gaps for the CoE transition. | Accelerates workforce readiness by identifying critical skill gaps and enabling targeted training for AI-enabled roles and CoE transition. |

IT Operations & Cybersecurity (4 Agents)

| # | Agent | What It Solves | Business Impact |
| --- | --- | --- | --- |
| 18 | AI Service Desk | 4,200+ tickets per month with 40% repeat issues resolved manually — Wipro HOLMES deflects repeat tickets through self-service AI, auto-resolves known issues, and routes complex tickets with full context, targeting 60% L1 deflection. | Achieves up to 60% L1 ticket deflection, reducing support costs and improving resolution times while enhancing user experience through faster, self-service issue resolution. |
| 19 | IT Operations Automation | Repetitive IT operations workflows — patching, monitoring, provisioning, and incident response — consuming significant engineer time — Wipro WINGS automates these workflows intelligently, freeing IT capacity for strategic EOS support. | Achieves up to 60% L1 ticket deflection, reducing support costs and improving resolution times while enhancing user experience through faster, self-service issue resolution. |
| 20 | OT Threat Detection | OT cybersecurity relying on perimeter defenses with no AI-based anomaly detection — agent monitors OT network telemetry for unusual communication patterns, unauthorized device connections, and control system anomalies aligned to IEC 62443 threat models. | Improves threat detection speed and accuracy across OT environments, reducing cyber risk exposure and enabling early identification of anomalies aligned to IEC 62443 standards. |
| 21 | Shadow IT Discovery | 60+ unmanaged tools running critical business processes with no visibility, no governance, and no security — agent scans network traffic and endpoint data to identify shadow applications, classify risk, and feed the rationalization disposition framework. | Identifies and reduces unmanaged applications, lowering security risk and enabling application rationalization from 120+ systems to a controlled, governed portfolio. |

Solution Coverage Summary

- 21 AI agents deployed across 6 business domains

- Covers 100% of Sadara’s critical operational functions

- Designed for phased rollout aligned to data readiness and business priority

- Fully integrated with enterprise and OT systems

# Implementation Approach

Wipro’s implementation approach for Sadara’s EOS is structured as a four-wave, 60-month transformation program designed to deliver measurable business value at every stage.

Each wave builds on the last: a rationalized application landscape enables a reliable data foundation, a reliable data foundation enables trusted AI agents, and trusted AI agents enable a self-sustaining, intelligent enterprise. This phased approach reduces implementation risk while accelerating time-to-value, ensuring Sadara realizes early wins without compromising long-term scalability.

Wipro’s approach avoids front-loading complexity, ensuring Sadara begins to realize tangible business outcomes within the first six months.

This delivery model is directly aligned with Wipro’s outcome-based commercial framework, where investment is tied to verified business outcomes rather than effort. Platform setup is delivered through a fixed-fee model, AI agent deployment is aligned to KPI achievement, and managed services ensure continuous optimization and value realization through Month 36 and beyond.

Program at a Glance

|  | Wave 0 Foundation & Discovery | Wave 1 Platform Foundation & Early Value | Wave 2 AI Scale & Cross-Domain Integration | Wave 3 Optimization & Autonomous Operations |
| --- | --- | --- | --- | --- |
| Period | Months 1–3 | Months 4–12 | Months 13–24 | Months 25–60 |
| Focus | Foundation & Discovery | Platform Build | Scale & AI Expansion | Optimization & Self-Sufficiency |
| Agents Live | 0 | 4–5 Pilot | 12–16 Production | 21 Full Portfolio (By M36) |
| Commercial | Fixed setup fee | Outcome-based KPI payments | Outcome + Managed Services | Managed Services + Innovation Fund |

## Wave 0 – Foundation & Discovery

Before building anything, Wipro establishes the ground truth — a clear picture of what exists, what it costs, and what must change. Wave 0 is entirely non-disruptive: no systems are changed; no data is moved. It produces the artefacts that every subsequent wave depends on.

Application Rationalization — Wipro APM Methodology

Wipro applies its Application Portfolio Management methodology to perform automated discovery of Sadara's full application landscape — all 120+ systems inventoried, dependency-mapped, and scored against five dimensions: business value, technical health, integration complexity, compliance risk, and total cost of ownership. Every application receives a disposition: Keep, Migrate, Retire, or Consolidate. Quick wins — shadow IT tools with no active owner and high maintenance cost — are retired within Wave 0 itself, delivering immediate budget relief before any AI is deployed.

Discovery Workshops

Wipro-led structured workshops across all six functional domains — Manufacturing, Supply Chain, Commercial, Finance, HR, and IT. Conducted in English and Arabic. Workshop outputs: current-state workflow documentation, pain point validation, a scored AI use case backlog of 50+ candidates, and stakeholder alignment on priority use cases for Wave 1.

Data Source Identification and Data Catalog

Every data source across SAP, Salesforce, Workday, PI Historian, SCADA, ServiceNow, ETRM, and 60+ standalone tools is catalogued — with data classification, quality assessment, owner identification, and integration complexity rating. The data catalog becomes the input for Wave 1 ingestion pipeline design.

Smart i Safe Pre-requisites

Site survey of priority manufacturing units to identify camera placement, OT network topology, DMZ requirements for PI Web API deployment, RFID infrastructure status, and edge hardware specifications. Output: a deployment readiness report per unit with a sequenced rollout plan.

RACI and Governance Setup

Wipro establishes the full program governance structure in Wave 0. RACI matrix, Strategic Steering Committee charter, PMO cadence, milestone gate criteria, and escalation paths. The program health dashboard is configured and accessible to Sadara leadership from Day One.

Outcome: Sadara knows exactly what it has, what it will keep, and what will be built. No surprises in Wave 1.

## Wave 1 – Platform Foundation & Early Value

Wave 1 builds the foundational technology platform on which all AI agents will run. By Month 12, Sadara has a governed data Lakehouse, a live ingestion pipeline, Smart i Safe operational in priority plants, and 4–5 pilot AI agents in production. This is the first point at which outcome-based KPI payments begin.

The purpose of this wave is to establish the core data and integration foundation required to enable enterprise AI, while delivering the first set of high-impact use cases to demonstrate measurable business value.

Wipro Intelligence — Databricks Lakehouse

Wipro's Databricks partnership delivers the unified data Lakehouse. Medallion architecture (Bronze, Silver, Gold) is configured with Delta Live Tables pipelines which is the automated ETL declarative build, and MLflow for model registry. The Lakehouse is live and ready for ingesting data by Month 6.

Wipro Intelligence — IDMC Data Ingestion and Governance

Informatica IDMC is deployed as the ingestion and governance layer, connecting to all enterprise source systems via native connectors — SAP via RFC/BAPI/OData, Salesforce and Workday via REST APIs, PI Historian via PI Web API through the DMZ. Field-level cleansing, PII masking under Saudi PDPL, and master data golden records are configured before any data lands in the Lakehouse. Both live streaming and batch ingestion patterns are operational by Month 9. The Lakehouse platform is provisioned and configured by Month 6. IDMC ingestion pipelines are live, and data begins landing in Bronze by Month 9.

Wipro Smart i Safe — Priority Manufacturing Units

Smart i Safe is deployed at the highest-priority manufacturing units identified in Wave 0 — edge AI hardware (NVIDIA Jetson) installed, camera zones configured, PPE detection models deployed, and IoT/RFID sensors commissioned. Restricted zone monitoring and PPE compliance alerts are live. Safety incident records flow automatically to SAP EHS. This is Wipro's fastest visible impact — safety AI on the plant floor within 6 months of program start.

Pilot AI Agents — 4 to 5 Use Cases

With governed data available in the Lakehouse by Month 9, Wipro builds the first 4–5 production AI agents in Months 10–12. Priority agents are selected from Wave 0 uses case backlogs based on data readiness and business value: Predictive Maintenance (Manufacturing), AI Service Desk (IT Operations via Wipro HOLMES), Demand Sensing (Supply Chain), and Automated Reconciliation (Finance). Each pilot agent undergoes formal Model Registry review before production deployment.

Data Ingestion Pilot Run and Validation

A structured validation exercise confirms data quality, latency, and completeness across all ingestion pipelines before AI agents begin consuming Gold data. Data stewards from each functional domain sign off on Silver and Gold layer quality metrics. Any gaps identified are remediated before Wave 2 agent build begins.

Key Activities

- Deploy the Unified Data Fabric, integrating priority enterprise systems (SAP, ETRM, Salesforce) with selected OT data sources

- Establish secure data ingestion pipelines, governance frameworks, and data quality controls

- Configure the initial AI platform environment, including model orchestration and agent frameworks

- Develop and deploy priority AI agents focused on high-value use cases such as predictive maintenance and IT operations

- Implement initial dashboards and user interfaces to enable real-time visibility and interaction

Outcome:

- A scalable, governed data foundation supporting both IT and OT integration

- First set of AI agents deployed into production environments

- Real-time data visibility across selected operational and enterprise domains

- Demonstrated reduction in unplanned downtime and improvement in IT service efficiency

## Wave 2 – AI Scale & Cross-Domain Integration

Wave 2 is the delivery wave — the largest in scope and the highest in value creation. All 21 domain AI agents are built and deployed. Smart i Safe extends to all 26 manufacturing units. Sadara's internal Centre of Excellence is established and begins operating. By Month 24, Sadara's CoE independently delivers AI use cases without Wipro-led development.

The purpose of this wave is to scale AI capabilities across multiple business domains and enable cross-functional decision-making by integrating enterprise and operational data into a unified intelligence layer.

Smart i Safe — All 26 Manufacturing Units

Smart i Safe is extended from priority units to the full fleet of 26 manufacturing units. Edge AI hardware is deployed at each unit, computer vision models are tuned to unit-specific environments, and the full safety monitoring capability — PPE compliance, restricted zone detection, fatigue indicators — is operational enterprise-wide. All safety events feed the central Lakehouse for pattern detection across the full plant.

All Domain AI Agents — Full Portfolio

Wipro builds the remaining 16–17 AI agents across all six functional domains, bringing the live portfolio to 21 agents in production by Month 24. Each agent is built against governed Gold data, reviewed through the Model Registry, and deployed with the full approval engine and audit trail. The Service Bus (SAP BTP Integration Suite) handles all agent-to-enterprise system writebacks.

Centre of Excellence — Establishment

Wipro establishes and staffs Sadara's internal AI Centre of Excellence in a three-phase transition. In Wave 2, the CoE is co-led by Wipro and Sadara's nominated AI Director — ratio shifts progressively from 80% Wipro in Month 13 to 60% Sadara by Month 24. Sadara secondees shadow every model build and deployment. By Month 24, the CoE independently delivers at least 3–5 use cases without Wipro-led development.

Training Program

Three-level training program runs from Month 15: Level 1 AI Awareness for all 16,000 employees (2-hour e-learning, English and Arabic), Level 2 AI User training for 4,000+ primary users (8-hour role-specific workshop), and Level 3 AI Builder certification for CoE and power users (multi-week program). Minimum 50 certified internal AI practitioners by Month 24.

API Monetization and Innovation

AI agents and data models built for Sadara are evaluated for commercial potential beyond Sadara's own operations — export of anonymized AI models and APIs to other chemical companies in the GCC through a managed API marketplace. Wipro's Innovation Fund (10% of TCV, governed quarterly) funds emerging technology pilots: robotics for plant inspection, AR/VR maintenance guidance, and advanced edge AI capabilities.

Key Activities

- Expand the Unified Data Fabric to include additional OT systems, enterprise applications, and external data sources

- Deploy additional domain AI agents across Supply Chain, Commercial, Finance, HR & Safety, and Cybersecurity

- Enable cross-domain data integration to support end-to-end use cases (e.g., production planning aligned with supply chain demand and pricing strategies)

- Enhance AI models with advanced analytics, scenario simulation, and forecasting capabilities

- Integrate AI agents into existing workflows, applications, and user interfaces to support real-time decision-making

- Strengthen governance frameworks for data, models, and AI lifecycle management

Outcome:

- Enterprise-wide data integration across critical business and operational systems

- 21 AI agents to actively support decision-making across multiple domains

- Seamless interaction between business functions through shared data and insights

- Increased automation of planning, forecasting, and operational processes

## Wave 3 – Optimization & Autonomous Operations

The purpose of this is to advance Sadara toward a self-optimizing, AI-driven operating model by enabling continuous improvement, autonomous decision support, and enterprise-wide intelligence.

Wave 3 transitions from delivery to sustained excellence. Wipro shifts from developer to managed services partner. Sadara's CoE owns AI development. The program delivers board-level transparency and continues reducing technical debt — converting the 65% maintenance IT budget toward innovation.

Managed Services — 24/7 Platform Operations

Wipro provides SLA-backed managed services covering the full EOS platform: Lakehouse operations, ingestion pipeline monitoring, AI agent model monitoring and drift detection, ESB management, edge device health monitoring, and infrastructure management. All within KPI-linked SLAs. Monthly managed services fee covers all operations, model retraining execution, and CoE advisory support.

Board AI Dashboard

A real-time board-level AI dashboard is delivered — showing enterprise AI adoption metrics, value delivered to date, risk posture, and strategic alignment with Vision 2030 and JV partner (Aramco/Dow) reporting requirements. Updated automatically before every board meeting. CFO, COO, and CEO each have a role-specific view. The dashboard is Sadara's single source of truth for AI program governance at the executive level.

Tech Debt Reduction — Continuous

App rationalization, running continuously since Wave 0, reaches its target in Wave 3 — 120+ applications reduced to 40–60 core systems. SAP ECC 6.0 migration advisory (Wipro's S/4HANA practice) is provided as part of the advisory component. Dual Salesforce instances consolidated. Shadow IT eliminated. The IT budget allocation shifts from 65% maintenance toward 40% maintenance and 60% innovation — freeing $50M+ annually for strategic investment.

CoE Full Independence

By Month 36, Sadara's CoE is fully Sadara-owned and operated — 15–20 internal AI/ML engineers, data engineers, product managers, and an AI ethics officer, all certified through the Train-the-Trainer program. The CoE serves as Sadara's internal AI consulting function — business units bring problems, the CoE designs and delivers solutions. Wipro remains as managed services partner but does not lead new use case development.

Key Activities

- Expand AI agent capabilities to support advanced optimization, prescriptive decision-making, and autonomous recommendations

- Enable closed loop decisioning, where AI insights automatically trigger actions within enterprise systems and workflows

- Introducing advanced scenario modeling and simulation across production, supply chain, and commercial operations

- Implement continuous learning pipelines to refine AI models based on real-time data and outcomes

- Establish enterprise-wide AI governance, monitoring, and performance management frameworks

- Scale the AI Center of Excellence to support ongoing innovation, model lifecycle management, and business alignment

Outcome:

- AI-driven and self-sufficiently optimization across all major business functions

- Closed-loop processes enabling faster and more consistent execution

- Continuous improvement of models and decisions based on live operational data

- Reduced reliance on manual intervention and institutional knowledge

Wave 3 enables Sadara to operate as a continuously improving, intelligence-driven enterprise. Decisions are no longer reactive or siloed — they are optimized in real time across functions, balancing production efficiency, cost, demand, and risk. This results in sustained cost reductions, improved asset utilization, enhanced safety outcomes, and greater operational resilience.

Success Metrics

- Increased asset utilization and production efficiency

- Reduction in operational variability and process deviations

- Improved margin optimization across commercial and supply chain operations

- Reduction in manual decision-making and intervention

- Continuous improvement in AI model accuracy and performance

## Alignment with the Outcome based commercial model

The wave structure is deliberately aligned with Wipro's outcome-based commercial philosophy — Sadara does not pay for delivery milestones alone, it pays for verified business outcomes.

Implementation

| Component | Wave | Structure | What Triggers Payment |
| --- | --- | --- | --- |
| Fixed Platform Fee | 0 –1 | 100% of Platform TCV (incl. Hardware and Software) Hardware – One-Time fee Software – Annual Subscription fee | Program governance established, discovery complete, platform infrastructure provisioned including hardware and software |
| Fixed Implementation Fee | 0-3 | 30% of the Implementation TCV Advance Payout | Team Structing and Mobilization, Platform Set up, GPMO Governance model set up, Escalation & Steering committee set up, Project templates and artifacts establishment. |
| Outcome-Based Fee | 1 – 3 (Months 4 – 36) | 70% of the Implementation TCV Quarterly Payout | Independently verified KPI achievement vs baseline: downtime reduction, ticket deflection, close day improvement, incident reduction |
| Innovation Fund | 1 - 3 (Months 1 – 60) | The Innovation Fund is included in the Base Contract of TCV. It is earmarked for AI, automation, and emerging technology initiatives and governed through quarterly approvals. | Emerging technology pilots, robotics, AR/VR, responsible AI experiments, API monetization |

Managed Services

| Component | Wave | Structure | What Triggers Payment |
| --- | --- | --- | --- |
| Managed Services | 3 (Months 25 - 60) | Monthly SLA | 24/7 platform operations, model monitoring, retraining, CoE advisory support |

## Timeline – 60 months

The transformation roadmap below illustrates how Sadara progresses from foundational capabilities to enterprise-scale AI adoption, with measurable value delivered at each stage.

| Activity | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36-60 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| App Rationalization |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Discovery & Data Catalog |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Smart i Safe Pre-req |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| IDMC Platform Build |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Databricks Lakehouse Build |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Data Ingestion (Live/Batch) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Smart i Safe — Priority Units |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Pilot AI Agents (4–5) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Smart i Safe — All 26 Units |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| All Domain AI Agents (21) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| CoE Establishment |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Training Program |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| API Monetization / CoE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Managed Services |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Board AI Dashboard |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Tech Debt Reduction |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

Each colored bar represents active delivery in that month.

Wave 0 (dark), Wave 1 (blue), Wave 2 (green), Wave 3 (red).

App Rationalization runs continuously across all 60 months — it is not a prerequisite gate, but a parallel program triggered by and aligned to each wave's delivery milestones.

# Delivery & Governance

Wipro operates a multi-tier governance model across the 60-month EOS program, designed for large-scale, outcome-linked AI transformation where accountability, transparency, and independent verification are non-negotiable.

Governance is not a reporting structure — it is the mechanism through which Sadara retains strategic control, Wipro maintains delivery accountability, and every AI model is validated before entering production.

This model ensures disciplined execution, controlled risk, and sustained value realization throughout the transformation.

## Multi-Tier Governance

Four governance tiers operate simultaneously — each with defined authority, cadence, and decision rights. This governance structure ensures that strategic direction, operational execution, and AI model oversight are tightly aligned, enabling controlled delivery and accountable value realization at every stage of the EOS program.

| Governance Level | Leadership Structure | Cadence | Decision Authority |
| --- | --- | --- | --- |
| Strategic | Steering Committee (Sadara CEO/COO, Wipro Engagement Partner, CFO, CTO) | Monthly | Approves wave transitions, budget changes (>5%), scope adjustments, and resolves escalations |
| Program | Program Management Office (Wipro Delivery Lead, Sadara Program Director) | Weekly PMO reviews, bi-weekly health reporting, monthly financial tracking | Manages RAID log, approves milestone gates, allocates resources, and oversees vendor coordination |
| AI Governance | AI Model Board (Wipro AI Lead, Sadara AI Director, Chief Data Officer) | Per deployment and monthly review | Approves model production release, conducts bias and compliance validation, sets drift thresholds, and exercises kill-switch authority |
| Operational | Domain Leads (Wipro Workstream Leads, Sadara Domain Owners) | Daily standups and weekly sprint reviews | Prioritizes backlog, oversees use case delivery, and ensures knowledge transfer to CoECoE knowledge transfer |

Strategic Steering Committee

The Strategic Steering Committee is jointly chaired by Sadara’s CEO/COO and Wipro’s Engagement Partner — the most senior Wipro executive accountable for the program.

The committee meets monthly and holds authority over:

- Wave transition approvals

- Budget reallocations and adjustments (>5%)

- Scope changes and escalation resolution

- Sub-contractor onboarding and removal

Quarterly sessions align EOS program outcomes with Sadara’s Vision 2030 strategic KPIs and joint venture reporting requirements (Aramco/Dow), ensuring executive-level visibility without unnecessary meeting overhead.

Program Management Office — Wipro PMO Framework

Wipro’s PMO operates a structured delivery assurance framework, serving as the single source of truth for program execution.

Key capabilities include:

- Weekly RAID log management

- Bi-weekly delivery health reporting

- Monthly earned value and financial tracking

The PMO is proactive in execution management:

- Resource bottlenecks are identified and addressed within 48 hours

- Schedule variances trigger formal corrective action plans

- Budget deviations exceeding 5% are escalated to the Steering Committee within one business day

The PMO ensures disciplined execution, transparency, and continuous alignment across all workstreams.

AI Model Governance Board

A dedicated AI governance body operates independently from the PMO, ensuring strict control over AI model lifecycle and production readiness.

This board, comprising Wipro’s AI Lead, Sadara’s AI Director, and the Chief Data Officer, serves as the sole authority for AI model approval.

Key responsibilities include:

- Approval of all AI models prior to production deployment

- Bias and compliance validation

- Continuous monitoring of model performance and drift

- Enforcement of kill-switch protocols when required

The board meets on demand for model deployment decisions and conducts monthly portfolio reviews. As the AI Center of Excellence matures, governance transitions to Sadara leadership, with the AI Director assuming chair responsibilities by Month 24.

Prime Contractor Accountability

Wipro serves as the single point of accountability for the EOS program, covering all delivery components including sub-contractors, platform providers, and technology partners.

All third-party activities are governed under Wipro’s vendor management framework, ensuring consistent quality, accountability, and performance standards.

Sadara benefits from:

- A single contractual relationship

- A unified escalation path

- One accountable delivery partner

This model simplifies governance, reduces risk, and ensures end-to-end ownership of outcomes.

## Milestone Gates & Controlled Progression

Wipro’s EOS program is governed through a series of formal milestone gates, ensuring that each phase is validated, controlled, and value-aligned before progressing. These gates enforce discipline across delivery, data readiness, AI deployment, and business outcomes — preventing premature scaling and ensuring measurable success at every stage.

### Wave Transition Gate Framework

| Gate | Wave | Exit Criteria | Approver |
| --- | --- | --- | --- |
| G0 Foundation | 0 → 1 | App disposition complete. Data catalog signed off Smart i Safe site survey approved. RACI agreed. Governance operational | Steering Committee + Sadara CTO |
| G1 Platform | 1 → 2 | Lakehouse operational. All ingestion pipelines validated. Data quality sign-off by domain stewards. Smart i Safe operational at priority units. 4–5 pilot agents in production | Steering Committee + Sadara CDO + VP Manufacturing |
| G2 Scale | 2 → 3 | All 21 agents in production. Smart i Safe across all 26 units. CoE independently delivering use cases. 50 certified practitioners. KPI targets independently verified by external auditor | Steering Committee + Sadara CEO + Independent Auditor |
| G3 Sustain | 3+ | CoE fully independent. Managed services SLAs met. Board AI Dashboard live.120+ apps reduced to 40–60. IT maintenance budget ≤40% | Steering Committee + Sadara Board sign-off |

This gate-based approach ensures that each phase of the EOS transformation is validated against technical readiness, business outcomes, and governance standards before advancing.

### AI Deployment Gate — Add Framing Line

All AI models deployed within the EOS must pass a formal AI Deployment Gate, ensuring they meet strict standards for performance, fairness, security, and operational readiness prior to production release.

| Gate Criterion | What Is Assessed | Minimum Bar |
| --- | --- | --- |
| Accuracy & Performance | Model accuracy, precision, recall, F1 against hold-out test dataset. Compared to the baseline (pre-AI) performance. | Meets or exceeds defined accuracy threshold per use case. No regression vs baseline. |
| Bias & Fairness Audit | Fairness assessment across demographic segments for HR, procurement, and commercial models. Documented methodology and results. | No statistically significant bias detected. Remediation plan documented if marginal. |
| Security Validation | Model signing and integrity check. Adversarial input testing. Access control validation. Encrypted inference confirmed. | Model cryptographically signed. No adversarial vulnerabilities. RBAC enforced. |
| Explainability & Grounding | Tier classification confirmed (1/2/3). Reasoning chain validated by domain expert. Hallucination and grounding tests for LLM-based agents. | Tier 1/2 — full explainability. LLM agents — grounding verified, no fabrication on test set. |
| Human Override & Kill-Switch | Kill-switch mechanism tested. Human override workflow validated end-to-end. Override logging confirmed. | Kill-switch suspends agent in <30 seconds. Override logged with identity and rationale. |
| Operational Readiness | Rollback plan documented and tested. On-call runbook created. Model owner assigned from Sadara team. Monitoring alerts configured. | Rollback tested successfully. Sadara owner named. Monitoring live before go-live. |
| Continuous Training Plan | Retraining trigger defined (drift threshold). Retraining pipeline tested. Data refresh cadence agreed with domain owner. | Drift threshold set. Automated alert configured. Retraining pipeline validated. |
| KPI Tracking Setup | Baseline KPI measurement confirmed. Target KPI agreed with Sadara. Measurement methodology documented and accepted by independent auditor. | Baseline locked. Target agreed. Measurement method auditor-approved before go-live. |

Tier 1: safety-critical models require Sadara's COO sign-off in addition to the AI Model Governance Board.

Tier 2: Financial models require CFO delegate approval.

Tier 3: Productivity models are approved by the AI Director. This approval hierarchy is strictly enforced, with all decisions documented in the Model Registry including identity, timestamp, and rationale. All approvals are logged with identity, timestamp, and rationale in the Model Registry.

This structured gating framework ensures that Sadara’s AI transformation is not only scalable, but also controlled, auditable, and aligned to enterprise risk and compliance standards.

## Program Health Dashboard

Wipro’s Program Health Dashboard is a real-time, role-specific intelligence platform — not a static status report. Accessible 24/7 to all governance tiers and provides a single source of truth for program health, financial performance, AI model status, and business value delivery.

Built on the EOS platform itself, the dashboard serves as the first production use case of Wipro Intelligence — demonstrating the platform’s capabilities while actively governing the transformation.

| Dashboard Module | Key Insights | Primary Audience |
| --- | --- | --- |
| Workstream Milestone Tracker | RAG status per workstream and wave. Planned vs. actual milestone performance. Upcoming gates and blockers. | PMO · Steering Committee · Sadara Program Director |
| Plan vs Actual | Schedule variance per workstream. Budget burn rate vs. forecasted spend. Earned value analysis. Forecast at completion. | PMO · CFO · Wipro Engagement Partner |
| Deviation Register | All scope, schedule, and budget deviations logged with root cause, impact assessment, and resolution action. Change request status. | Steering Committee · PMO · Sadara CTO |
| Risk Register | Minimum of 25 active risks tracked with probability, impact, mitigation strategy, residual risk rating, and owner. Updated weekly. | All governance tiers — risk posture visible to Steering Committee |
| AI Model Health | Per-model drift score, validation status, retraining cadence, accuracy trends, and override rates, with automated alerts on threshold breaches. | AI Model Board · Sadara CDO · CoE |
| KPI Value Tracker | Outcome KPIs vs baseline and target — downtime reduction, ticket deflection, closed days, safety incidents. Updated monthly based on independently audited KPI data. | Steering Committee · CFO · Independent Auditor |
| AI Adoption Heatmap | Agent usage rates across all 26 units and 6 domains. Override rates per agent. User NPS by role. Adoption cold spots flagged for change management intervention. | PMO · Change Management Lead · CoE |

This dashboard ensures complete transparency across delivery, financial performance, AI operations, and business outcomes — enabling real-time decision-making and proactive intervention at every governance level.

Unlike traditional reporting models, this dashboard enables Sadara leadership to move from retrospective reporting to real-time, AI-driven program governance.

# Workshop Program

Wipro’s workshop program is not a series of presentations — it is a structured co-design framework that builds organizational understanding, captures domain knowledge, and progressively transfers capability from Wipro to Sadara’s internal teams across all delivery waves.

Each workshop has a defined output, a named owner, and a direct linkage to program deliverables, ensuring that every session contributes directly to measurable outcomes.

| Workshop Type | Wave | Timeline (Months) | Key Output | Ownership |
| --- | --- | --- | --- | --- |
| Discovery | 0 | 1–3 | Prioritized AI use case backlog (50+ candidates with scoring) | Wipro + Sadara domain leads |
| Design Thinking | 1 | 4–9 | Experience prototypes aligned to prioritized use cases | Wipro + business users |
| Architecture | 1 | 2–6 | Architecture Decision Records — jointly authored | Wipro + Sadara EA + OT teams |
| Executive Alignment | All | 3, 6, 9, 12, 15, 18, 21, 24, 27, 30, 33, 36 | Strategic review deck + JV partner briefings | Wipro Engagement Partner |
| Train the Trainer | 2–3 | 12–30 | 50 certified internal AI practitioners (Sadara CoE) | Wipro CoE Lead + Sadara AI Director |

## Discovery workshop

Wave 0: Months 1–3

Wipro facilitators sit with teams across all six functional domains — plant operators, finance analysts, procurement staff, traders, HR managers, and IT support — documenting actual operational workflows rather than system-defined processes. Output is a scored AI use case backlog of 50+ candidates with business value, data readiness, and implementation complexity rated for each. Conducted in English and Arabic.

## Design Thinking Workshop

Wave 1: Months 4–9

For each prioritised AI use case, Wipro facilitates a joint session with business users and technical teams together. Experienced plant operators — 20+ years — are central participants, not passive reviewers. Output: experience prototypes showing exactly what the operator, analyst, or manager sees, what decision the AI augments, what happens when the AI is wrong, and how they override it. Institutional and experiential knowledge is captured and embedded within AI-driven workflows — not replaced.

## Architecture workshop

Wave 1: Months 2–6

Technical deep dives with Sadara's enterprise architecture, OT, and security teams. Output is jointly authored Architecture Decision Records — ensuring a collaborative, co-authored approach rather than a vendor-led approval model. Dedicated OT integration sessions with DCS engineers and PI System administrators are held separately — these are not IT conversations. Security boundary definitions and integration pattern agreements are co-authored and signed off before any build begins.

## Executive Alignment

Quarterly: All Waves

Quarterly strategic sessions with Sadara's C-suite — not status updates. CFO gains clear visibility into ROI and financial impact. COO reviews live demonstrations of operational AI capabilities. CEO validates alignment with Vision 2030 strategic objectives. Separate briefing packs are prepared for Aramco and Dow parent company stakeholders, tailored to each JV partner's technology standards and reporting expectations.

## Train the Trainer

Wave 2–3: Months 12–30

Wipro trains Sadara's CoE team to independently run discovery workshops, design use cases, build models, and deploy to production. Minimum 50 certified internal AI practitioners by Month 30. Wipro dependency shows a documented declining curve — Wipro dependency is expected to decline progressively across Waves 2 and 3. Any deviation from this trajectory triggers a structured remediation plan to ensure successful knowledge transfer.

# Assumptions & Exclusions

- Sadara provides access to all source systems, including SAP, Salesforce, Workday, PI Historian, ServiceNow — with necessary API credentials and integration permissions within 30 days of program start.

- Sadara's IT and OT teams participate actively in Wave 0 discovery workshops and architecture sessions — including DCS engineers, PI System administrators, and domain business leads.

- Platform access to be provided by Sadara.

- SAP ECC 6.0 remains operational throughout the programme. S/4HANA migration, if initiated, runs as a parallel programme. SAP S/4HANA migration execution is excluded from this scope — Wipro provides advisory and readiness support only.

- PI Web API is available or can be enabled on Sadara's existing OSIsoft PI System within Wave 0. DMZ provisioning and firewall rule configuration is executed by Sadara's network security team. Wipro implements EOS components only — penetration testing of existing OT, DCS, or SCADA infrastructure is excluded.

- Wipro's delivery obligations assume data meets minimum quality thresholds defined during Wave 0. If not, remediation timelines and outcomes are subject to revision.

- Sadara nominates a dedicated AI Director and 2–3 full-time secondees to the CoE from Month 1. Wipro's knowledge transfer obligations are contingent on Sadara resourcing the CoE as agreed. Recruitment and employment of Sadara's internal CoE team is Sadara's responsibility.

- If organizational participation is passive, AI adoption outcomes are not Wipro's sole accountability.

- KPI baselines are jointly agreed and locked before any AI agent goes live. Post-lock baseline disputes are resolved through the independent auditor. Regulatory approvals required for AI model deployment — Saudi NCA, NDMO, SDAIA — are Sadara's responsibility; Wipro provides compliance documentation and evidence.

- Camera installation, RFID infrastructure, and physical edge hardware deployment across 26 manufacturing units requires site access coordination by Sadara's HSE and facility management teams. Any integration with third-party systems not listed in the Wave 0 data source inventory is subject to change control.

- Any hardware, software and platform enablement or purchase as part of the Innovation Activity is subject to discussion and CR.

- Travel, accommodation, and visa costs for Wipro onsite resources in Saudi Arabia are either included in the commercial model or reimbursed by Sadara at actuals — to be agreed in the contract schedule. Custom ABAP remediation of Sadara's 340+ existing programs, and business process reengineering outside defined AI use cases, are excluded and subject to separate scoping.

- Post-Month 60 managed services, platform licensing renewals, and hardware refresh are excluded from this contract and subject to a separate renewal agreement. Arabic content localisation beyond what is specified in this proposal is subject to separate pricing.

# Wipro Team - Tentative

| Role | Wave | Number of Resources | Resource Responsibilities | Location Onsite / Offshore |
| --- | --- | --- | --- | --- |
| Engagement Manager (Senior Executive) | All | 1 | Single point of accountability. Owns client relationship, commercial governance, and strategic advisory. | Onsite |
| Program Principal / Director | All | 1 | End-to-end delivery ownership. PMO governance, milestone gates, RAID log, and financial tracking. | Onsite |
| Enterprise Architect | 0–1 | 1 | Owns 7-layer EOS architecture. Architecture Decision Records, integration patterns, and technology selection. | Onsite |
| AI / ML Architect | 0–2 | 1 | Designs agentic AI platform, agent orchestration framework, and MLOps pipeline. Governs all 21 agent builds. | Offshore |
| Sr. Data Architect | 0–2 | 1 | Owns Medallion Lakehouse design, IDMC pipeline architecture, and Unity Catalog governance framework. | Offshore |
| OT / IIoT Sr Architect | 0–1 | 1 | Designs OT-IT integration — DMZ, PI Web API, edge AI deployment across 26 units. IEC 62443 compliance. | Onsite |
| SAP Integration Lead (Senior Consultant) | 1–2 | 1 | Owns SAP connectivity — ECC BAPIs, OData, S/4HANA readiness, and SAP BTP Integration Suite configuration. | Offshore |
| Cybersecurity Lead (Senior Consultant) | 0–3 | 1 | Zero trust architecture, OT security boundary, NCA ECC compliance, and AI model security controls. | Onsite |
| Smart iSAFE Lead (Senior Consultant) | 1–2 | 1 | Deploys Smart iSAFE across all 26 units — edge CV models, IoT/RFID sensors, PPE detection, and safety workflows. | Onsite |
| Data Engineering Lead (Senior Consultant) | 1–3 | 1 | Builds and manages IDMC pipelines, Delta Live Tables transformations, PII masking, and data quality framework. | Offshore |
| Data Engineers | 1–2 | 3 | Develops ingestion pipelines, Bronze-Silver-Gold transformations, and master data golden records. | Offshore |
| AI / ML Engineers | 1–2 | 4 | Builds, trains, validates, and deploys domain AI models across all 6 functional domains. | Offshore |
| ESB / Integration Engineers | 1–2 | 2 | Configures SAP BTP Integration Suite — protocol translation, approval engine, audit logging, and agent write-back. | Offshore |
| Domain Functional Leads (Senior Consultant) | 0–2 | 3 | Subject matter experts bridging business domain knowledge with AI agent design across Manufacturing, Supply Chain, and Finance. | 2 Onsite 1 Offshore |
| MLOps Engineer | 2–3 | 1 | Manages model lifecycle — training pipelines, retraining triggers, drift detection, and deployment automation. | Offshore |
| CoE Lead (Senior Consultant) | 1–3 | 1 | Establish Sadara's AI CoE and manage Wipro-to-Sadara capability transfer across all three CoE phases. | Onsite |
| Change Management Lead (Senior Consultant) | 0–3 | 1 | Leads the 16,000-person change program — impact assessment, communications strategy, and adoption measurement. | Onsite |
| Change Management Analysts | 1–2 | 2 | Supports training delivery, stakeholder engagement, adoption heatmap tracking, and bilingual communications. | Onsite |
| PMO Analyst | All | 1 | Maintains program health dashboard, RAG status, plan vs actual tracking, and risk register. | Offshore |
| Responsible AI Officer (Senior Consultant) | 0–3 | 1 | Owns AI ethics framework, bias monitoring, tiered risk classification, and regulatory compliance mapping. | Offshore |
| QA / Testing Lead | 1–3 | 1 | Owns AI deployment gate reviews — accuracy validation, bias audits, security testing, and operational readiness. | Offshore |
| Total |  | 31 |  | 11 |

Onsite / Offshore Split: 35% / 65% Onsite peaks during Wave 0 and Wave 1 for discovery, architecture, and plant-level Smart iSAFE deployment. Offshore scales in Wave 2 for agent build and data engineering. Wave 3 transitions to a lean managed services team.

Please refer to Artifact Wipro Team for resumes and credentials.

# Center of Excellence

The Center of Excellence (CoE) is the mechanism through which Sadara becomes self-sufficient in AI delivery and governance. Established from Day 1, progressively staffed, and fully independent by Month 24, the CoE is not handed over at program end — it is built alongside delivery.

The CoE evolves across three structured phases, transitioning ownership from Wipro-led delivery to full Sadara independence.

Phase 1 — Embedded (Months 1–12)

Wipro leads (80%) with 2–3 Sadara secondees embedded from Day 1 — enabling hands-on capability development through active participation rather than passive observation. Every model built and every deployment made has a Sadara shadow. By Month 12, Sadara's AI Playbook is published — covering how AI projects are initiated, built, deployed, monitored, and retired — written in Sadara's context, not a Wipro template.

Phase 2 — Hybrid (Months 13–24)

Co-led by Sadara's AI Director and Wipro's AI Lead. Ratio shifts to 60% Sadara / 40% Wipro. By Month 24, the CoE independently delivers a minimum of 10 AI use cases into production without Wipro-led development — a defined contractual milestone, not an aspirational target. The CoE begins functioning as Sadara's internal AI consulting body — business units bring problems, the CoE delivers solutions.

Phase 3 — Independent (Months 25–60)

Fully Sadara-owned. Wipro provides managed services only — no new use case development. Minimum 15–20 internal resources: AI/ML engineers, data engineers, product manager, change manager, and AI ethics officer — all certified. The CoE governs AI across the enterprise: approving models for production, monitoring bias and drift, managing the model registry, and enforcing responsible AI standards.

This phase establishes Sadara as a self-sustaining AI-driven organization, with internal ownership of model development, deployment, and governance across the enterprise.

This structured CoE model ensures that capability is transferred progressively, dependency is reduced intentionally, and Sadara is equipped to scale AI independently beyond the EOS program.

# Change Management

Many AI programs encounter challenges at the adoption stage — where the technology is functional and models are accurate, yet user adoption remains limited. At Sadara’s scale, with over 4,200 employees and 12,000 contractors, successful transformation requires more than deployment — it requires behavioral change.

Change management is therefore the defining factor between a successful AI transformation and underutilized technology investment.

Change Impact Assessment Before any AI deploys, every use case is documented — who is affected, how daily workflow changes, what skills are needed, what is lost, what is gained. This is conducted as a transparent and structured assessment, ensuring clarity and alignment across all impacted roles. Workforce segmented into four groups, each with a distinct engagement strategy: Champions, Pragmatists, Sceptics, and Resistors. Resistors are listened to — their objections reveal real problems the AI must address.

Operator-Centric Design Experienced plant operators — 20+ years — co-design AI interfaces and validate recommendations. When an operator sees their own expertise reflected in AI logic, adoption follows naturally. The change program is designed with operators, not for them — ensuring that AI solutions reflect real-world expertise and drive natural adoption. Adoption target: 80%+ of targeted users actively changing their decision-making process within 6 months of deployment — not just logging in.

Communication Strategy Structured programme from Day 1 through Month 60. CEO town halls explaining why AI matters. Floor-level sessions where operators ask hard questions. Regular AI Stories — short case studies of specific people in specific roles using AI to make better decisions. All communications in English and Arabic. All communication is delivered in clear, domain-relevant language that resonates with chemical engineers and plant operators, avoiding unnecessary technical jargon — language that resonates with chemical engineers and plant operators.

Training Programme Three levels — no exceptions:

- Level 1 — AI Awareness: All 16,000 employees · 2 hours · what AI means for my job.

- Level 2 — AI User: 4,000+ primary users · 8-hour role-specific workshop · how to use and override AI.

- Level 3 — AI Builder: CoE and power users · multi-week certification · design, build, and deploy AI.

Adoption Measurement Beyond login counts — decision quality improvement, time saved, user NPS, and override rate trends. Reviewed monthly. Real-time adoption heatmap across all 26 units and departments identifies cold spots for targeted intervention.

This structured approach ensures that adoption is measurable, sustained, and directly linked to business outcomes — not just system usage.

## Change Order Governance

All changes to scope, timeline, or cost are governed through a formal Change Order process designed to ensure transparency, control, and alignment across all stakeholders.

Any deviation from the agreed scope is treated as a Change Order (CO), which is formally assessed, estimated, and mutually approved prior to execution. This ensures that all changes are evaluated for impact on delivery timelines, cost, and business outcomes.

A Change Control Board (CCB), comprising representatives from Sadara and Wipro leadership, is responsible for reviewing and approving all change requests. The CCB evaluates:

- Business impact

- Cost implications

- Timeline adjustments

- Risk considerations

No change proceeds to implementation without formal approval.

### Change Order Process

The flow-diagram given below explains the steps involved in the CO Process:

All changes are managed through a structured process supported by standardized tools and tracking mechanisms.

Key Components:

- Change Order Form (COF) formal request documentation

- Change Order Tracker — centralized repository for all changes

Each change is assigned to a unique Change Order ID and tracked throughout its lifecycle — from identification through approval, implementation, and closure.

The Change Order Tracker serves as the single source of truth for all changes and is continuously updated by the Wipro Project Manager, with regular reporting to Sadara stakeholders.

# Communication and Coordination

Wipro’s communication and coordination model is designed to ensure continuous alignment, transparency, and rapid decision-making across all levels of the EOS program. The framework integrates executive reporting, operational coordination, and real-time escalation mechanisms to support a complex, multi-stakeholder transformation.

Meeting Cadence

A structured meeting cadence ensures alignment across all governance levels:

- Daily standups at the workstream level to track progress and resolve immediate blockers

- Weekly program reviews led by the PMO to monitor delivery status, risks, and dependencies

- Monthly Steering Committee meetings for strategic oversight, KPI tracking, and escalation resolution

- Quarterly executive sessions aligned to Vision 2030 objectives and JV reporting requirements

Reporting Structure

Program reporting is centralized and standardized to provide a single source of truth:

- Real-time visibility through the Program Health Dashboard

- Weekly delivery status reports covering milestones, risks, and dependencies

- Monthly financial and KPI reporting aligned to outcome-based metrics

- Executive summaries tailored for Sadara leadership and JV stakeholders

Escalation Mechanism

A structured escalation model ensures rapid resolution of issues:

- Workstream-level escalation within 24 hours

- PMO-level escalation for cross-functional risks and delays

- Steering Committee escalation for critical issues impacting scope, cost, or timeline

All escalations are logged, tracked, and resolved through the centralized program governance framework.

Documentation Standards

All program artifacts are maintained in a structured and auditable format:

- Architecture Decision Records (ADRs)

- AI model documentation and validation reports

- Change Order documentation and approvals

- Governance and compliance records

This ensures full traceability and alignment with audit and regulatory requirements.

Risk Management Integration

Communication is tightly integrated with risk management processes:

- Weekly risk reviews and updates to the Risk Register

- Visibility of risk posture across all governance levels

- Proactive communication of mitigation actions and impact assessments

# Ethics, Risks & Responsible AI

Wipro’s approach to AI at Sadara is grounded in responsible, transparent, and controlled deployment. Given the scale, complexity, and safety-critical nature of Sadara’s operations, AI governance is treated as a core component of the EOS program — not an afterthought.

The framework ensures that every AI capability is auditable, compliant, and aligned with enterprise risk standards while enabling innovation at scale.

Responsible AI Policy

A formal Responsible AI Policy is established within the first 90 days of the program, co-designed with Sadara’s legal, HSE, and compliance teams.

The policy covers:

- Fairness and bias mitigation

- Transparency and explainability

- Accountability and governance

- Data privacy and security

- Safety and operational integrity

The policy is published as a CEO-approved, enterprise-wide standard — not an internal guideline.

Tiered Risk Classification

All AI models are classified into one of three tiers prior to deployment:

- Tier 1 — Safety-Critical
Full explainability, human approval before action, mandatory kill-switch, and real-time monitoring

- Tier 2 — Financial / Regulatory
SOX-compliant audit trail, regulatory-grade logging, and annual third-party validation

- Tier 3 — Productivity / Advisory
Standard logging, user feedback mechanisms, and opt-out capability

This classification ensures appropriate controls are applied based on risk and impact.

Bias Monitoring and Fairness

Continuous monitoring is applied across all HR, procurement, and commercial AI models to detect and mitigate bias.

Quarterly fairness audits are conducted using documented methodologies, with remediation actions defined and tracked to closure.

Model Lifecycle Governance

All AI models are managed through a centralized Model Registry, which tracks:

- Model purpose and ownership

- Training data sources

- Performance metrics and validation history

- Approval of workflow and deployment status

- Drift detection and retraining triggers

No model operates in production for over 90 days without formal revalidation.

Regulatory Compliance

All AI capabilities are mapped to applicable regulatory frameworks, including:

- Saudi NCA, NDMO, SDAIA, and PDPL

- IEC 62443 and RC 14001

- Aramco and Dow digital security standards

Compliance is designed to be fully auditable and testable, ensuring alignment with both national and joint venture requirements.

AI Incident Response

A structured AI incident response framework is established to manage any consequential model failure.

This includes:

- Defined severity levels and escalation paths

- Immediate rollback and containment procedures

- Root cause analysis and corrective actions

- Regulatory notification where required

Tabletop exercises are conducted at least twice per year to validate readiness.

All Tier 1 and Tier 2 systems include frictionless human override mechanisms, enabling operators to reject AI recommendations without operational penalty.

# Strategic Advisory

Wipro’s advisory role differentiates a transformation partner from a technology integrator. Embedded across all four waves — not as a separate workstream — it ensures that every technology decision is aligned to Sadara’s business strategy, joint venture governance obligations, and Vision 2030 mandate.

Operating Model Design Defines Sadara’s AI-enabled future-state operating model, including:

- Which decisions become AI-augmented

- How roles evolve

- What new capabilities are required

Delivered as a documented Blueprint by Month 6 and updated quarterly. Designed to align with both Aramco and Dow operating philosophies.

Technology Roadmap Provides a forward-looking, 5-year technology perspective delivered annually, covering:

- Platform evolution

- Edge AI and advanced analytics expansion

- Robotics and automation opportunities

- Emerging technology impacts specific to Sadara’s petrochemical context

Focused on actionable strategy — not generic market insights.

Organisational Design and Skills Delivers a structured workforce transformation plan, including:

- Role evolution and workforce impact assessment

- Skills gap analysis and capability development roadmap

- Hiring and reskilling strategy

Co-designed with HR and aligned to local workforce considerations.

Tech Debt Reduction Roadmap Establishes a business-case-driven roadmap to rationalize Sadara’s application landscape from 120+ systems to a streamlined core of 40–60 applications.

This advisory is continuous across all waves, ensuring that rationalization decisions remain aligned to business value and operational priorities.

Competitive Intelligence Provides quarterly benchmarking against industry peers, including SABIC, Aramco Digital, and Dow.

Insights include:

- Comparable AI and digital deployments

- Cross-industry best practices

- Strategic positioning relative to competitors

Board Readiness Supports Sadara’s executive and board-level communication through:

- AI governance briefings aligned to board expectations

- CFO-ready ROI articulation for JV stakeholders

- Real-time AI dashboard updates prior to board meetings

# Commercial Model

## WIPRO’s Outcome based commercial philosophy

Wipro does not charge Sadara for effort. It charges for results. Every commercial component is tied to a measurable business outcome — independently verified, not self-certified. If the AI does not deliver, Wipro does not get paid in full. A transformation partner that shares the risk of failure is a partner invested in ensuring success.

## Commercial structure

| Component | Wave | Structure | What Triggers Payment |
| --- | --- | --- | --- |
| Fixed Platform Fee | 0 –1 | 100% of Platform TCV (incl. Hardware and Software) Hardware – One-Time fee Software – Annual Subscription fee | Program governance established, discovery complete, platform infrastructure provisioned including hardware and software |
| Fixed Implementation Fee | 0-3 | 30% of the Implementation TCV Advance Payout | Team Structing and Mobilization, Platform Set up, GPMO Governance model set up, Escalation & Steering committee set up, Project templates and artifacts establishment. |
| Outcome-Based Fee | 1 – 3 (Months 4 – 36) | 70% of the Implementation TCV Quarterly Payout | Independently verified KPI achievement vs baseline: downtime reduction, ticket deflection, close day improvement, incident reduction |
| Innovation Fund | 1 - 3 (Months 1 – 60) | The Innovation Fund is included in the Base Contract of TCV. It is earmarked for AI, automation, and emerging technology initiatives and governed through quarterly approvals. | Emerging technology pilots, robotics, AR/VR, responsible AI experiments, API monetization |

## ROI Calculation

Wipro's ROI model is built on Sadara's own operational data — not generic industry benchmarks. Every assumption is stated and every sensitivity tested across three scenarios.

Value Drivers

- Unplanned downtime reduction across 26 manufacturing units

- IT budget freed from maintenance spend to innovation.

- Supply chain logistics and inventory optimization.

- Financial close acceleration

- Safety incident reduction and RC 14001 compliance gains

Payback Period Payback achieved within 18–24 months from programme start — driven primarily by downtime reduction and IT budget liberation in Waves 1 and 2

# Sovereignty & IP Framework

## Intellectual Property Ownership

| Asset | Owner | Terms |
| --- | --- | --- |
| AI models trained on Sadara data | Sadara | Full ownership — perpetual, irrevocable |
| Wipro pre-existing IP, frameworks, accelerators | Wipro | Retained by Wipro — perpetual license granted to Sadara |
| Joint innovations developed during program | Negotiated | Case-by-case — agreed in writing before development begins |
| Open-source components used in delivery | Disclosed | Full inventory provided — Sadara approval required before use |
| Sadara data — all forms | Sadara | Wipro has no right to use, retain, or commercialize beyond program delivery |

Wipro does not acquire any rights to Sadara's operational data, process knowledge, or business intelligence through the delivery of this program. All AI models, pipelines, and configurations built on Sadara data are Sadara's property from the moment of creation.

## Data sovereignty

All Sadara data — structured, unstructured, OT sensor, financial, and personal — remains within the Kingdom of Saudi Arabia at all times. No data transits outside the Kingdom without explicit written approval from Sadara's CPO and CTO.

Compliance obligations met simultaneously:

- Saudi PDPL — personal data handled with consent, minimization, and full subject rights

- NDMO — data classified, governed, and retained per national data management standards

- NCA ECC — cybersecurity controls applied across all data in transit and at rest

- Aramco and Dow standards — JV parent data handling requirements satisfied in parallel

All offshore Wipro delivery resources access Sadara data only through controlled, audited, and role-gated environments — no raw data is transmitted to offshore locations. Offshore teams work on anonymized or synthetic datasets during development and testing phases.

Upon program completion or contract termination, Wipro certifies full data deletion from all Wipro-managed environments within 30 days — with written confirmation to Sadara's CPO.

# Case Studies & References

Please refer to Artifact Case Studies and References